## Electronic Records Management
Electronic Records Management | 2004-2005 Investment Budget Proposal
Commitment item/GL |  | Description | Amount 2004 | Amount 2005 | Future annual maintenance Amount 2006 | Comments - eg basis of rate, for maintenance contract date of renewal, any assumptions, etc.
6800 Other staff costs-A25
681010 | TFT (professional)
681020 | TFT (GS) |  |  | 0 | 0
681020 | TFT (GS) | ERM Sr. Project Assistant [G-7] | 84000 | 88000 | 92000 | Provide DPP-ERM administrator support for users at NYH, ongoing training and demonstrations to new users, advice on conversion formats and tests, validity checks for user entered data, record type connection and update of retention and destruction tables including origination office signoffs on record series destruction recomendations.
682010 | Overtime for TFT(GS) | Uninstall RAMP-TRIM 4.3 & Install 5.1 | 1000 | 1000 |  | Clien Workstations - update
6020 Staff training-
661010 | Staff & TFTs training
661020 | Travel on training
661010 | User training (preparation, material, delivery, customers/users)
7000 Consultants- 710000 | Subject matter experts
711010 or 711030 | Interfaces support-indvdls or Inst
711010 or 711030 | Conversion of Data | Conversion & Migration of data related to TRIM 4.3 to 5.1, CF-RAMP01 and OED Chron Log | 6000 | 1000 |  | Consultant support SQL Anywhere to Oracle and copy object stores, for OED Chron ISAM to Oracle
"711010 or 711030 | User interface | Update Reports and Forms TRIM 4.3 to 5.1 | 2000 | 2000 |  | Set up data entry forms - to reflect 4.3 basic and add 5.1 ease of use features
"711010 or 711030 | Location Table synchronisation | Person/Post/work unit table -synchronise with import / update with similar table used for PROMS and FLS update. | 3000 | 1500 | 1500 | Kasi to provide latest info on status. Was done for WANG to TRIM conversion
"711010 or 711030 | Interfaces development-indvdls or inst. | Menu and Views for MS Access DB -appraisal Decision Assist.tool | 7500 | 1500 | 1500 | Consultant support take basic tables provided by WGARM consult & integrate in TRIM context or simple menu structure for easy update in access or export data
QA
711010 or 711030 | Admin training | TRIm Context DPP System Administrators and ITD application Support | 2000 | 2000 | 2000
711010 or 711030 | User Training | Previous RAMP-TRIM users, new features; complete first time user, Design of Special training and implement for first user groups. | 13000 | 13000 | 5000 | special modules for New users - full [Adapted from basic 4.3 version Series, folders, boxes, Items, Attachments, Top-drawer], Search using Web access
711010 or 711030 | User Manuals | UNICEF RAMP-TRIM user manual upgrade & Unicef specific help file | 6000 | 4000 | 2000
711010 or 711030 | Confirming major Record Series | In participating divisions, update or validate basic forms using TRIM for easy update of the record series inventory form, including volumes and priority actions etc. for groups of records | 25000 | 25000 | 5000 | follow up to 2003 WGARM apprisal decision Project.
711010 or 711030 | Confirming Work Flow between work units related to record series | Identify dependencies and special workflow relationships, share record between sections or units, alerts etc. | 13000 | 13000 |  | See what functions could be assited.e.g auto by e-mail alert if action required or completed
711010 or 711030 | Confirm Retention/ Destruction for major record Series identified during WGARM phase 1 exercise and Gap analysis. | Make record destruction / retention proposals and justification. Secure agreements and record conflicting appraisal values/conditions if exceptions exist, update schedules | 36000 | 42000 | 7500 | follow up to 2003 WGARM apprisal decision Project.
711010 or 711030 | interoperability between related desktop systems and trim |  | 10000 | 20000
711010 or 711030 | Interfaces development-indvdls or inst.
711010 or 711030 | Additional hours
711010 or 711030 | Develop training material, delivery
711040 | Consultants travel
7200 Travel -
720000 | Travel for staff members
720000 | Travel for TFTs
7300 Operating expenses-
731010 and/or 731020 | Documentation (editing and/or printing)
731100 | Enterprise management costs
731090 | Development
731090 | Support
731090 | Testing
734040 | WAN requirements
734040 | LAN requirements
737050 | Backup media
737050 | Security
737050 | Data cleansing/upload
737050 | Contingency for growth
737050 | Downtime costs
737050 | Transition costs
737050 | Release costs
737070 | Software distribution costs
737050 | Quality assurance
732080 | Electricity, airconditinioing
732010 | Office space
7400 Furniture and equipment-
742020 | Enterprise management costs
742020 | Hardware | RampTRIM-Databases Server [for RAMCF01 & OEDChron] | 10000 |  |  | Replacement for NT641A13 [e.g Compaq 370 G3 2.4Ghz or better. Additional 6 36.4 GB pluggable drives, Additional 1024MB RAM
742020 | Hardware | HP-NSI-TRIM-Scanning Conversion PDF Autostore Server | 8000 |  |  | Used for TIFF conversion to PDF and transfer to RAMP-TRIM db. Replacement for NT641A125 [e.g G3 2.4Ghz or better. Additional 1024MB RAM]
742020 | Hardware | RAMP-TRIM Work Group server |  | 8000 |  | work-group server recommended by tower above certain number of users or processes
742020 | Hardware | RAMP-TRIM event processing, advanced query, indexing an searching Server |  | 10000 |  | possibily also used of older data stores with extra drives
742020 | processing
742020 | storage/backup
742020 or 742060 | network equipment
742020 | desktop/laptop | Laptop for RAMP-TRIM system admin management | 4000 | 4000 |  | Use with copy of RAMP-TRIM DB to Trouble shoot when requied away from office, advanced searches and for demos to Divisions
742020 | LAN compatable Digital Sender | HP Digital Sender 9100C [or better -2003 cost aprox $2,200 per scanner] LAN & RAMP-TRIM worthy; 15 ppm, 2 sided with manual turnover of stack | 14000 | 14000 |  | one per floor , additional as needed by specific division
742020 | Barcode readers | Hand held with compatable software installed | 1000 | 1000 |  | for use with tracking files, boxes and inventories for RAM, DRU, & Div/section users to borrow as needed
742020 | Barcode readers | Stationary Reader station with sorftware to be installed | 1000 | 3000 |  | for DRU, Mail Receiving, LICRC
742020 | LAN compatable Digital Sender | Scanner [High speed -duplex] LAN & RAMP-TRIM worthy | 10000 | 7000 |  | one per building for high volume scanning- Duplex feed [2sided] 50 ppm or better need
742020 | peripherals
742020 | configuration and installation
742030 | Software purchase | RAMP-TRIM New Licenses is version 5.1 [32 concurrent users full upgrade] | 79000 | 95000 |  | may eventully break up future license for read only and full update in order to have more read only and less full user for similar price. Have to then administer different type of license etc. For NY site license the cost could be around $200,000 spread over 4 years or two years ifs prefered if commitmnet in 2003
742030 | Software purchase | NSI Auto Store software interface between TRIM & Hp Digital Serder [$200] per sender] | 1000 | 1500
742030 | Software purchase | Back end Database for RAMP-TRIM [now SQL-A will move to oracle] | 38000 |  |  | upgrade from Current SQL Anywhere to Oracle recommended by ITD , it is cost per server or processor at present [2005 extra cost only if use an extra processor or server]
742030 | Software maintenance | Annual Maintenance and upgrades for Oracle DB back end | 8500 | 8500 | 8500
742030 | Software maintenance | TRIM Software Maintenance and upgrades - annual -32 user per year is now 10,000 | 12000 | 12000 | 24000 | in addition to currently 10,00 per year [32 concurrent users full upgrade is part of our license - includes all upgrades and top-drawer and webdrawer] maintenance for site license in NY could eventually be = $40,000; assumes pay increase in maintenance fee year upgrade numbers added.
742030 | Software maintenance | Maintence and upgrades for NSI Auto Store software interface between TRIM & Hp scanner-Digital Sender | 5000 | 7000 | 2000 | run this process on one server. Auto Store Software [Modules Barcode, PDF Conversion etc]
741010 & 742010 | Furn. & office equip(UPS, aircond. Etc.)
742020 & 742030 | Firewall (Hardware & Software)
742020 & 742030 | Redundancy (Hardware & software)
| Total |  | 400000 | 385000 | 151000