Registered for sharing with WGARM as: UN-CS-RAI-USAA-DB01-2005-00065

Piloting in UNICEF Assisted Programmes

Content:

A.  Introduction	2

B.  The Most Important Findings	3

C.  Scope and Methodology	4

D.  Findings	5

D.1. The Use of Piloting as a Programme Strategy	5

D.2. Review of Selected Pilot Projects	8

# A.  Introduction

Piloting is a significant strategy for UNICEF Programme Cooperation.  Pilot projects represent a particular form of research that test strategies, interventions, and policy options for large-scale adoption in national development plans and policy. Well-designed and documented pilot projects can address the issue of “scaling up”, and can generate knowledge and lessons for wider application.

The 2004 UNICEF Programme Policy and Procedure Manual contains guidance on Pilot Projects (Chapter 6, Section 16). The guidance is intended to assist in designing, formulating, and providing support to the implementation of pilot projects. It is suggested that the reader of this report familiarizes her or himself with this guidance. The purpose of this report is to further illustrate the guidance note on piloting and to contribute to the discussion on knowledge generation and management in UNICEF.

Part B of this report provides the most important findings and conclusions.

Part C is an overview of the findings of the report, with some examples of pilot projects to illustrate various aspects of the piloting methodology.

The materials used in this report were reviewed and analyzed by Celine Liu, intern in the Programme Guidance Unit, Division of Policy and Planning.  All descriptions of pilot projects have been drafted based on materials received from the Country Offices. The descriptions are meant for illustrative purposes, and may not reflect complete documentation possible held by Country Offices, or completely describe the supported interventions.

We would like to thank all Country Offices for their participation in this exercise.  Please share any comments or queries you may have on this report, or on any of the specific piloting guidance issues raised in this report, with Detlef Palm, Programme Guidance and Quality Assurance Section (PGQA) in the Division of Policy and Planning, dpalm@unicef.org.

# B.  The Most Important Findings

- Less than 40% of UNICEF country offices report that they conducted pilot projects in the 2003.  Pilot projects can generate evidence and contribute convincingly to knowledge generation, national policy development and advocacy. Piloting makes strategic use of limited UNICEF resources, but is not very widely used as a programming strategy.

- Reporting on Pilot Interventions, in Country Office Annual reports, is inadequate. Only one sixth of the incidences where piloting was mentioned communicated even superficially the nature of the project, the lesson learned, or experience or evidence sought. The organization is not kept aware of investments made for pilot initiatives, which could possibly benefit from regional or global coordination, support and follow up.

- Documentation on pilot projects is often inadequate. Many offices were not able to provide definite documentation on their pilot projects, due to perceived inadequacy of existing documentation, staff transfers, or other reasons. A successfully completed pilot project can only make a case for the effectiveness and viability of larger policy recommendations or plans, if  - and only if -  it provides solid evidence, usually in form of credible and well presented documentation. Otherwise, opportunities for strengthening advocacy and organizational learning are lost.

- Virtually every pilot project lacked clear and concise statements about what was to be achieved or demonstrated. Pilot projects are a strategic way to use UNICEF’s limited resources to test the feasibility and/or the effectiveness of an intervention or policy decision. Without clear description of the intervention, assumptions, planned results or tested policy changes, it is not possible to establish causalities between the intervention and the documented change. It will also be difficult to propose realistic plans for scaling up, or changes to existing national or local policies.

- Less than half of the examined pilots had established a baseline.  Many examined pilots conducted initial assessments, including capacity assessments and other inquiries, but only half of those ended up with a baseline against which change could be measured.

- All examined pilots established mechanisms to monitor progress in the interventions, and about half reported on completed evaluations.

- A cost analysis of pilots is not consistently done. Without a separation of the costs of research and costs of implementation, it will be difficult to estimate the costs of a scaled up intervention, or the cost implications of a proposed policy change. It will be more difficult to “sell the idea”, if Governments are unable to take informed decisions that include cost implications.

- All examined pilots were successful, to some degree, in achieving their planned outcomes.  This is a surprise. Possibly, failed pilots were not reported. It should be noted that also unsuccessful pilot generate lessons to be learned, that could be worth sharing.

# C.  Scope and Methodology

A keyword search was conducted of all 2003 Country Office Annual Reports (n=129).  Where “pilot” or “piloting” was mentioned, respective paragraphs in the Annual Reports were read to identify at least minimal description of the projects, and to obtain some assurance that the basic conditions for a “pilot project” were met. Country offices who provided, in the COARs, the most complete descriptions of pilot projects were contacted to supply any additional existing documentation on the pilot.  These documents, which could include project design documents, proposals, baseline assessments, evaluations, final reports, or documents describing national policy changed on the basis of successfully completed pilot projects, were used to re-construct project descriptions that were then used for the purposes of this research.

Of the 13 offices that were contacted to supply additional documentation on 15 different pilot project, 10 offices responded with written project materials that were extensive enough for further review.  Additionally, 3 projects were brought to the attention of the Programme Guidance Unit for inclusion in this review, although the pilots were not mentioned in the 2003 COARs.  This resulted in a total of 14 pilots that were reviewed in close detail, based on any existing and submitted documentation from the country offices (One extensively documented pilot project from Uruguay was left out of close analysis due to language limitations).

All text in this report has been based on materials received from the Country Offices, unless otherwise noted.  In these cases, hypotheses, conclusions, and implementation processes have been paraphrased when they were not clearly stated in the original documentation.

The author and the staff of the Programme Guidance Unit are aware that, while the initial sample of 129 Country Office Annual Reports was sufficiently large, the final sample of 14 pilots selected for closer review is rather small, and may not allow immediate generalization of the findings. It is hoped, nevertheless, that the discussion of the findings will indicate trends, complement existing guidance on pilot projects contained in the UNICEF Programme Policy and Procedure Manual, and be helpful for those planning to initiate new or review existing pilot projects.

# D.  Findings

## D.1. The Use of Piloting as a Programme Strategy

Use of piloting. In 129 COARs (2003) that were reviewed, 99 different pilot projects were mentioned.  The 99 pilots occurred in 51 different countries. Some countries reported more than one pilot. The distribution of pilot projects was uneven across regions, and programme areas.

Of 129 Country Offices, 61% did not report a single significant pilot in the 2003 programming year; 32% of them conducted 1 or 2 pilots; 5% of them had 3-6 mentions of different pilot projects in their report, and 2% of the countries had between 7 and 9 different pilots conducted in the 2003 programming year.  Especially in an environment where Country Offices are increasingly required to contribute to national development debates and plans, including PRSPs or SWAPs, piloting should be realized as an important strategy for evidence-based policy advice, and to make strategic use of UNICEF resources. The large proportion of countries that did not report any pilot indicates that piloting is not universally considered a significant programming strategy.

Reporting on Piloting in Annual Reports. Of the 99 pilots mentioned in the 2003 COARs, only 15 communicate, even superficially, the nature of the project, the evidence sought or generated, or lessons learned. In other words, only one-sixth of the reported pilots provided sufficient information to arouse interest among the audience and to warrant further inquiry. Given the potential lessons that all pilots can provide, whether successful or not, pilots should be adequately documented in the COARs to share insights with other country offices, provide some functional organizational record, and enhance organizational learning.

Availability of documentation on pilot projects. Thirteen country offices were contacted and asked to submit further existing documentation of the 15 pilots mentioned in their respective Annual Reports.  Existing documentation could include project design documents, proposals, baseline assessments, evaluations, donor reports, other reports, or documents describing national policy changed on the basis of successfully completed pilot projects. Offices were asked not to create any new materials. Documentation could be submitted electronically or in hard copy. Given the “demonstration” or research nature of any pilot project, it was expected that documentation would be readily available, especially upon conclusion of a pilot project.

The responsiveness to this request varied widely, even within country offices that were asked to submit documents on more than one pilot project.

Notwithstanding the busy year-end time, many offices had a hard time to submit –presumably existing – documentation on pilot projects. Out of the 15 separate requests that were sent, 6 were addressed immediately, another 6 were addressed when the reminder was sent a month after the original request, and 3 offices did not provide any additional documentation. (The type and content of the submitted documentation is discussed later in this report).

The inability of some COs to submit pilot project documentation is worrying, and points towards some lack of rigor in project design, implementation, monitoring and documentation. A successfully completed pilot project will make a case—or provide evidence—for the viability and usefulness of larger policy recommendations or plans.  Therefore, one necessary output of any pilot project is a set of credible documentation that provides proof of the worth of an intervention, the effects of a proposed policy change, or of the correctness of the working hypothesis.  Not only is adequate documentation necessary for effective evidence-based advocacy, but is also contributes to organizational learning.  Given that a pilot project is a resource-intensive research undertaking, the resulting insights and lessons should not be limited to the length of a staff member’s tenure at the respective office.

Validation Status of Pilot Projects.  It was not possible to determine or even approximate the status of the 99 pilot projects mentioned in the Country Office Annual Reports. From those more closely examined, about one third each had either completed a formal evaluation, had completed another formal review or assessment, or had not yet completed any review or validation.

Distribution of Pilots across Organizational Priorities.  Distribution of pilots across organisational priorities follows – very roughly – proportional organizational spending in those areas. Exceptions are significantly lower piloting rate in Immunization (which has long-established and widely-tested programme strategies), and a significantly higher rate of piloting in Child Protection (the most recent and least-explored of UNICEF’s organizational priorities).

*   One-third of Child Protection pilot projects are aimed at reforming health care

** Only 1/5 of the pilots related to education are aimed specifically at bridging the gender gap between girls and boys.

The distribution of more closely-reviewed “notable projects” across programme areas is somewhat different. Notable pilot projects were more prominent in Child Protection, and less prominent in Early Childhood Development. There was no “notable” pilot project specifically addressing Girls Education. However, the small sample prohibits generalized conclusions.

Distribution of Pilots across Regions.  Of the 99 instances where Pilots were mentioned in the Country Office Annual Reports, country offices in the CEE/CIS region have conducted and reported on pilot projects more than offices from other regions.  A possible reason is their proportionally smaller budgets, although the same argument would apply to offices from Latin America and the Caribbean, too. Another reason could be the more recent establishment of programmes in CEE/CIS, and the need to either identify entirely new programme strategies, or to test the applicability of proven strategies from other regions in CEE/CIS countries.

In contrast, “notable” pilot projects – or pilot projects more thoroughly documented in the annual reports - occurred most frequently and with equal distribution in CEE/CIS, EAP and LAC countries. Country Offices in LAC were generally better in providing details about their pilots, while country offices in CEE/CIS and WCARO would need to work on their pilot descriptions.

## D.2. Review of Selected Pilot Projects

Based on responses to our request for pilot documentation a total of 15 pilots were examined in closer detail, with the aim to extract lessons that can help to improve piloting as a strategy for UNICEF programme cooperation.  The selected projects were reviewed for several components considered critical to the purpose of piloting, namely:

- A clear statement of the hypothesis, or point that the project is trying to prove;

- The existence of a baseline, in order to allow measurement of change;

- A clearly identified process of monitoring and validation;

- A cost analysis, separating the costs of research from the costs of the tested activities, to be able to estimate the costs of a scaled up initiative or policy change;

- The existence of a well presented document, credibly providing evidence that the activities suggested for scaling up or the suggested policy change will have the planned effect.

Hypothesis. Pilot projects are a particular form of “demonstration” or research project, and should therefore satisfy the quality criteria for scientific social research.  Thus, any preparation of a pilot project should set out with the formulation of the hypothesis, model intervention and assumption of cause and effect, or simply the point to be proven.  The project documents should clearly state the intervention, activities, or policy change that is being piloted, and the outcome that is expected to directly result from the tested intervention.  In no instance was the piloted intervention and expected outcome clearly stated; the hypothesis of the reviewed pilots were either overly complex or absent or embedded.

Complex Hypothesis Statements:  Several of the submitted pilots included multi-pronged and complicated statements about the intervention strategy and expected outcomes.  While solutions to children’s problems are not likely to be simple, a pilot is meant to demonstrate the causal relation between the tested intervention and the later observed outcome.

In this example, the multiple interventions and expected outcomes make it difficult to confirm which component is effective in improving any one of the three planned outcomes. Even if all outcomes would be achieved, activity 3) would perhaps have been sufficient, or perhaps activity 3) did not contribute anything.  Both interventions and planned results lack specifity that would allow measurement of success.  Moreover, in this particular case, the requisite ECD policy was already adopted prior to conducting this pilot, and the project appeared to be about exploring how to enact policy changes in contrast to testing the possible effects of proposed policy changes. Nevertheless, given the complexity of the objective (or hypothesis) statement extracted from the project documentation, the evaluation or validation of this project will be difficult.

At times one may expect more than one outcome to result from the tested intervention, and it might be possible to design a programme that will accomplish more than one objective at once.  However, with two somewhat distinct strategies (life-skill training and community based counselling) and two rather distinct outcomes (reduced infection and available support), it might be difficult to prove the worth and effectiveness of the tested interventions in relation to the planned outcomes.

Embedded, General, or Absent Hypothesis Statements: About four fifths of the reviewed pilot projects did not clearly define the intervention to be tested, or the expected outcomes.  Often, the statements of – and correlations between – a proposed intervention and its expected outcome were embedded in the narratives. The reader was left to extrapolate, from the general project description, what the project is intended to do, through what means, what the expected changes are and how those changes will be measured.

The project documentation gives only a minimal description of the Active Learning methodology itself, and it is not clear how it will address the deficiencies in the country’s educational system as described in project documentation.  Indicators for “increased school and community capacity to meet the learning needs of the student population” might be difficult to come by.

Hypothesis 4 is a good example and quite straightforward in what it is trying to demonstrate: Teachers and students will be more satisfied with the new curriculum than they were with the old one. Presumably, the objective measurement of improvement in learning achievement will be left to the Ministry of Education or other actors.

Baseline Assessment: A baseline is required to measure change, and to provide the evidence that the proposed activities or policy measures have the desired effect. Without the existence of a baseline, the effectiveness of a piloted intervention cannot be ascertained.

Less than half of the examined pilots had established a baseline.  Many examined pilots conducted initial assessments, including capacity assessments and other inquiries, but only half of those ended up with a baseline of key indicators relevant to the expected result.

While in this example from a post-conflict country one can measure or estimate immunization coverage among women, it is not clear whether any pre-campaign coverage rates were available. Even if they were, it will be difficult to attribute any possible significant increase in coverage to the specifics of the campaign, which included a mix of communication and other strategies.

The pilot project in example 6 conducted an initial assessment to determine the areas of highest incidence of adolescent offences in the country, but the assessment did not measure, for instance, the present existence and use of alternative correction services, community perceptions of alternative correction service, or typical rates of relapse among young offenders.

The pilot in example 7 demonstrates how a baseline can be established (through a survey) so that changes in the capacities of officials working in the institutions can be measured and documented. Ideally, care practices of  foster parents should also have been surveyed.

Monitoring and Validation: Twelve of the reviewed pilots described an ongoing monitoring system to document progress of the interventions. Six had conducted final evaluations, though the quality of evaluations would undoubtedly be compromised where an initial baseline was lacking.

It is important to recall the particular monitoring and validation requirements of pilot projects. If the pilot project is to make a case for scaling up certain interventions, it is especially important to accurately monitor the implementation of those interventions – basically to ensure that what is recommended for wider adoption was actually tested. Similarly, and given that the findings of a pilot project are usually meant to result in widely replicated initiatives or far reaching policy changes, the validation of a pilot project must establish a strong causality between cause (the tested intervention) and the effect (the expect change in social indicators, or behavioural or institutional capacity outcomes). Therefore, in addition to—or within—a formal evaluation, consideration should be given to triangulation of the findings and results. Evaluations should also identify mitigating or supporting circumstances that influenced the outcome of the pilot project.

The mechanisms for monitoring and validation varied with the context, as did the descriptions of the mechanisms themselves.  Some documents merely stated that monitoring was ongoing, while others were more detailed, listing the frequency of monitoring activities, data collection systems, and responsible parties.  One might expect that pilots who planned for a rigorous validation did better in designing other components, such as formulating a clearer hypothesis, provisions for a cost analysis (discussed later), or a clear vision for the national or sub-national policy or program to be influenced by the pilots.  However, within the small sample, there does not appear to be any such correlation. Instead, it appear that many pilot projects are rather “experimental” in nature, and details of interventions, objectives, and related advocacy are refined or developed during the process. Notwithstanding that rare cases might exist where “experimenting” might be necessary, one rather would expect a clear and detailed plan to be the norm for public spending.

Below are examples of the types of validation and monitoring mechanisms described in the reports.

Cost Analysis: Without a separation of the costs of research and costs of implementation, it will be difficult to estimate the costs of a scaled up intervention, or the cost implications of a proposed policy change. It will be more difficult to “sell the idea”, if Governments are unable to take informed decisions that include cost implications. However, a cost analysis of pilots is not consistently carried out. Only one in seven examined pilots offices provided a cost analysis for both the pilot as well as the expected costs of scaling up; less than half provided a cost analysis for the pilot project alone; among these, the detail supplied would not facilitate a fully informed decision by government.

Cost categories to be analysed in a pilot might include:  research, start-up costs, recurrent costs; evaluation costs and costs of documentation. Indirect costs may be incurred by government, communities, and households, and consideration should be given to how these will be measured.  Care should be taken that the project does not unintentionally shift the cost burden from government to poor communities and households.

Although the analysis for the scaled-up/national coverage remains somewhat general – including in terms of population covered or unit costs, the above analysis facilitates some understanding of the scope of the undertaking by a government interested in scaling up.

In the following example, it would be much more difficult for Government or programme partners to project the costs of replication of the piloted initiative:

Clearly, Offices that did not provide any cost analysis of their pilot project will face the challenge of advocating for scaling up or policy change without being able to estimate the financial burden on the country’s budget.

Documenting Evidence:  The type and extent of project documents provided for 15 pilot projects indicate that Country offices do not sufficiently document their projects to maximize their utility for broader advocacy initiatives and policy dialogue.  In response to a request for documents related to an office’s pilot, the following were received in addition to email dialogue:

| Proposal or design document | 2 |
| --- | --- |
| Baseline survey or initial assessment | 4 |
| Mid-term report | 2 |
| Final evaluation | 6 |
| Advocacy material | 3 |
| Donor report | 1 |
| Summary Presentation of the completed project | 0 |
| Policy documents detailing ensuing policy change | 1 |

While some offices submitted more extensive documentation and material than others, no office was able to submit all of the above listed documents.  Demonstration of the success of a pilot will be much more convincing with the existence and ready availability of such materials.

Results of Pilot Projects: Notwithstanding that the outcome will not always corroborate the tested intervention strategy, a pilot project will always generate findings: either positive (e.g. the interventions achieve the projected results at acceptable costs) or negative (e.g. the tested interventions have only a limited effect, or the intervention is not feasible, too costly, or has negative side effects).  While negative results may not support the effectiveness of the tested strategy, they have the potential for providing important information when supported through an evaluation at a pilot’s conclusion.  The lack of a causal relationship between an intervention and an expected outcome can provide new insight into the assumptions, context analysis, or other planning and design parameters.

Considering the above, together with the probability that not all pilots will be successful, it is surprising that every single pilot project more closely examined for this report claimed of being able to document a causal relationship between the tested intervention and the desired outcomes.  This was ascertained from ongoing or completed evaluations, and also based on programme expansions and national policy recommendations implemented at the termination of the pilot projects.

# Footnotes

One office decided that – though the pilot was mentioned in the Annual Report - the project was not planned or implemented with sufficient rigour, and that the results were not conclusive enough to be considered for review. It is worth pointing out that lessons can also be learned from unsuccessful interventions, including possible insights on the adequacy of the underlying analysis, assumptions about cause and effect, or the reasons for the failure of the proposed intervention to produce the planned outcomes.  “Negative” pilot experiences (e.g. the tested intervention has only a limited effect; it is not culturally accepted; it is too costly; or it has negative side-effects) can help to bring out broader generalization and lessons for similar programmes also in other countries, provided that the findings of such pilot programmes are clearly positioned within a description of their programming context.

One well documented pilot project from Uruguay was not closely examined, due to language limitations

In some cases the hypothesis was re-constructed by the author on the basis of documents provided by Country Offices.

One of the 15 reviewed pilots was submitted in proposal form, implementation had not yet begun

Of course, Country Offices may not have bothered to include “failed” pilots in their Annual Reports. As however indicated, even unsuccessful pilots can generate lessons.

# Text boxes

Child

25%

Education**

Pilots by Program Area (n=99)

“… there are no longer staff members around that were engaged in the entire development and implementation of the below mentioned activity and all staff responsible for this project are new. Therefore it is difficult for me to provide you with all the details and related reports required for a comprehensive overview of the activity.”

A Program Officer in response to a request for written material about a selected pilot

9%

HIV/AIDS

6%

Immunization

32%

Childhood

Early

28%

Protection*

Example 2, Hypothesis:  Providing training on life skills and supportive counselling through community circles will reduce the incidence of HIV infection among at-risk and out-of-school youth and support already infected or affected youth from the ages of 15-24 years.

Example 12, Cost implications:

a.    Pilot

- Research, design, monitoring, and validation: TA around US$ 600

Evaluation by Investigating consultant: US$ 2,500

- Implementation: US$ 6,700 for two years from 2001-2002

- Scaled up/national coverage:  Approximately US$100,000 per year with gradual reduction in the cost per commune, since intervention focuses on communication for behavioural changes and less on expenses for hardware such as drainage system, constructions etc.

Example 13, Costs:

a. Pilot

- City A: 100,000 USD consultancy fees, training costs, supplies, medicines, furniture

a.   Research, design, monitoring, validation: 40,000

b.   Implementation:60,000

- City B:  20,000 USD (no breakdown provided)

- City C:  10,000 USD (no breakdown provided)

b. Scaled up/national coverage: N/A

Example 7 Pilot Description:   A project to improve foster care at 8 Child Welfare Institute sites in 8 different cities and counties which represent various economic and development levels as well as urban and rural environments.  Project activities include: the development of a foster-care information dissemination program, the establishment of a foster care workstation, and the development of training materials and certification program for foster parents to improve parenting skills and educate on issues particular to foster parenting based on alternative care guidelines.

First Assessment/Baseline: Investigation to determine the general situation of targeted welfare institutions (including training and background of staff and life satisfaction of children) and the reasons for child abandonment

Example 6, Pilot Description: Offering juvenile offenders between the ages of 13 to 18 alternatives to imprisonment.  Alternatives consist mostly of community service, rehabilitation, and employment.  An overall socio-educational plan is designed by the adolescent and an assigned social worker, who helps to ensure that specific requirements are met.  The plan usually includes schooling, a community activity or source of employment, as well as individual, group, and family counselling.

First Assessment/Baseline:  studies conducted determining areas of highest incidence of adolescent offences in the country

Example 8, Validation:  formative evaluation (2002); final evaluation (September-November 2004); biannual monitoring reports on conducted activities

Example 9, Validation (ongoing):  project monitoring

Example 10, Validation:  Mechanism for ongoing monitoring assessment for case managers and staff

Example 11, Validation:

- Trimester reports submitted regularly to UNICEF

- Project validated through a regional publication on best practices in juvenile justice in the region

Example 3, Hypothesis:  Implementation of the Active Learning methodology in schools, facilitated by training of educators and educational staff, will increase school and community capacity to meet the learning needs of the student population and create active, effective schools.

Example 5, Pilot Description: A campaign to reduce maternal and neonatal tetanus among child-bearing aged women in 8 major cities and 4 rural districts.  This campaign supplements the Expanded Program on Immunization (EPI), National Immunization Day (NID), and measles campaign to encourage targeted women to receive the required three doses of TT, thereby decreasing the incidence of tetanus.

First Assessment/Baseline:  none available for the campaign

Example 4, Hypothesis:  The introduction of the new curriculum into the country’s educational system will improve the quality of education and enhance the teaching/learning process, as reported by students and teachers.

Example 1, Hypothesis:  The establishment of: 1) a specific model of home/community-based care of young children; 2) community-based ECCD resource centres in every community in X and Y districts; 3) an inter-sectoral ECCD networking mechanism in the local community for establishing community-based child care and development services; 4) advocacy on the importance of the first three years of a child’s life and of holistic approaches for the care of children below 6 years; and 5) specified interventions in early detection and stimulation for children with disabilities; will result in a) improved parenting knowledge and skills for care of children below 3 years old; b) strengthened capacity of childcare providers for children 3-6 years old; and c) development of non-formal ECCD activities at community level.